## Проект 1
Calendar plan
Performers: |  | Yerlankyzy Anel, Akhmetova Bayan
Diploma Project: Website for monitoring and controlling the plans and tasks of government employees
% readiness | stage | period of execution | Doer
100% | Conduct a survey on the relevance of the topic | 16.09.2020-19.09.2020 | Yerlankyzy Anel
100% | Formation of technical specifications | 22.09.2020-26.09.2020 | Akhmetova Bayan
10% | Website design layout | 5.10.2020-19.10.2020 | Akhmetova Bayan
10% | Data analysis | 5.10.2020-12.10.2020 | Yerlankyzy Anel
0% | Website layout | 19.10.2020-02.11.2020 | Akhmetova Bayan
0% | Data collection | 12.10.2020-02.11.2020 | Yerlankyzy Anel
0% | Web-site programming | 02.11.2020-07.12.2020 | Akhmetova Bayan/Yerlankyzy Anel
0% | Content filling | 07.12.2020-14.12.2020 | Yerlankyzy Anel
0% | Project testing
0% | Additional works with web-site